## Feuil1
Page Link | Task | Component | Status | Start | End | Assign | Remarks
| Create | DB-Tables | Complete | 2017-03-20 | 2017-03-20 | Nick, Eros
| Create | BE-API | Complete | 2017-03-21 | 2017-03-21 | Nick, Eros
| Update | Dep-Angular | Complete | 2017-03-27 | 2017-03-27 | Nick | Update Angular 2 to Angular 4
| Design | Splash Page | assign | 2017-05-04 |  | RR
| Slice |  | Not Started |  |  | Albert, LA
| Function |  | Completed |  | 2017-05-03 | Eros
| Design Slice | Master Page | assign | 2017-05-09 |  | RR, Albert & LA | some modification needed, Manulife is too expanded and background color of navigation is too similar
| Slice |  |  | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Completed | 2017-04-03 | 2017-04-03 | Eros | testing image and video resource
1) MBPS DIS Overview | Resource | 01 - MBPS DIS Overview - DIS Mission Vision | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | assign | 2017-05-09 |  | RR, Albert & LA
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 02 - MBPS DIS Overview - Org Chart | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | assign | 2017-05-09 |  | RR, Albert & LA
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 03 - MBPS DIS Overview - Stratergies | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | assign | 2017-05-09 |  | RR, Albert & LA
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Not Started |  |  | Eros | Carousel functionality
| Resource | 04 - MBPS DIS Overview - Service Catalogue | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | assign | 2017-05-09 |  | RR, Albert & LA
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros
| Resource | 05 - MBPS DIS Overview - Programs - Aspire | For Verification |  |  | JP | Link or media?
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 06 - MBPS DIS Overview - Programs - Cares | For Verification |  |  | JP | Link or media?
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 07 - MBPS DIS Overview - Programs - Careers | For Verification |  |  | JP | Link or media?
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 08 - MBPS DIS Overview - Programs - Digerati | For Verification |  |  | JP | Link or media?
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 09 - MBPS DIS Overview - Programs - Motivate | For Verification |  |  | JP | Link or media?
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
2) Team Overview | Resource | 10 - Team Overview - Team Org Chart | Provided |  |  | JP
| Design |  | assign | 2017-05-09 |  | RR, Albert & LA | This is different per team
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 11 - Team Overview - Job Management Program - Team Services | Assign | 2017-05-09 |  | JP | This is different per team
| Design Slice |  | Not Started |  |  | RR, Albert & LA | This is different per team
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 12 - Team Overview - Job Management Program - Team Application | Assign | 2017-05-09 |  | JP | This is different per team
| Design Slice |  | Not Started |  |  | RR, Albert & LA | This is different per team
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 13 - Team Overview - Job Management Program - Team Tools | Assign | 2017-05-09 |  | JP | This is different per team
| Design Slice |  | Not Started |  |  | RR, Albert & LA | This is different per team
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
3) Leader' Video | Resource | 14 - Leaders Video - AVP Video | Pending |  |  | JP | Will be provided
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 15 - Leaders Video - Manager Video | Pending |  |  | JP | Will be provided
| Design Slice |  | Not Started |  |  | RR, Albert & LA | This is different per team
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 16 - Leaders Video - Team Lead Video | Pending |  |  | JP | Will be provided
| Design Slice |  | Not Started |  |  | RR, Albert & LA | This is different per team
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
4) MBPS DIS Tools | Resource | 17 - MBPS DIS Tools - OPT | Provided |  |  | JP
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 18 - MBPS DIS Tools - Workday | Assign | 2017-05-09 |  | JP
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Not Started |  |  | Eros | Carousel functionality
| Resource | 19 - MBPS DIS Tools - Khronos | Provided |  |  | JP
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
5) Policy | Resource | 20 - Policy - House Rules | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Assign | 2017-05-09 |  | Eros
| Resource | 21 - Policy - Vacation Leave | Assign | 2017-05-09 |  | JP
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Not Started |  |  | Eros | Carousel functionality
6) exam | Resource | 22 - Take the Exam | In Progress |  |  | JP | We already have a few, but will send you the list once completed.
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-24 | Eros, Nick, Albert | Pulling out 10 question from a pool of 10+
7)Credits | Resource | 23 - Credits | Pending |  |  | JP
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Not Started |  |  | Eros, Nick, Albert